## Sheet1
By: Eric Mulwa
2023-05-08
| Project Start Date | 2023-05-01 |  | GANTT CHART |  |  |  | 2023-05-08 |  |  |  | 2023-06-05 |  |  |  | 2023-07-03 |  |  |  | 2023-07-31 |  |  |  | 2023-08-28 |  |  |  | 2023-09-25 |  |  |  | 2023-10-23 |  |  |  | 2023-11-20 |  |  |  | 2023-12-18 |  |  |  | 2024-01-15
| Project Name: | Smart EV Wireless Charging System |  |  |  |  | Week starting | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22
# | Activity | Assigned To | Start | End | Days | Status | % Done
1 | Final Year Project Meeting 1 |  | 2023-05-03 | 2023-05-03 | 1 | Complete | 100% | bar: 2023-05-01
2 | Project Title Brainstorming and Presentation | Group Work | 2023-05-04 | 2023-05-18 | 11 | Complete | 100% | bar: 2023-05-15
3 | SEVWCS Model Design | Eric | 2023-05-18 | 2023-05-23 | 4 | Complete | 100% | bar: 2023-05-22
4 | Building SMART Objectives for the SEVWCS | Group Work | 2023-05-24 | 2023-05-29 | 4 | Complete | 100% | bar: 2023-05-29
5 | Choosing Project Components and Budgeting | Tom | 2023-05-25 | 2023-06-04 | 7 | Complete | 100% | bar: 2023-05-29
6 | Writing Project Concept Note and Presenting | Laura | 2023-06-01 | 2023-06-06 | 4 | Complete | 100% | bar: 2023-06-05
7 | Working on the revisons proposed by supervisor | Group Work | 2023-06-12 | 2023-06-25 | 10 | Complete | 100% | bar: 2023-06-19
8 | Smart EV Wireless Charging System Presentation | Group Work | 2023-06-24 | 2023-07-14 | 15 | Complete | 100% | bar: 2023-07-10
10 | Smart EV Wireless Charging System Proposal
11 | Chapter 1: Introduction | Laura | 2023-06-24 | 2023-06-27 | 2 | Complete | 100% | bar: 2023-06-26
12 | Background of the Study | Tom | 2023-06-24 | 2023-06-27 | 2 | Complete | 100% | bar: 2023-06-26
13 | Problem Statement | Eric | 2023-06-24 | 2023-06-27 | 2 | Complete | 100% | bar: 2023-06-26
14 | Justification | Group Work | 2023-06-28 | 2023-07-05 | 6 | Complete | 100% | bar: 2023-07-03
15 | Objectives | Group Work | 2023-06-29 | 2023-06-29 | 1 | Complete | 100% | bar: 2023-06-26
16 | Scope of the Study | Group Work | 2023-06-30 | 2023-07-12 | 9 | Complete | 100% | bar: 2023-07-10
18 | Chapter 2: Literature Review | Laura | 2023-06-24 | 2023-07-05 | 8 | Complete | 100% | bar: 2023-07-03
19 | Wireless Power Transfer WPT | Tom | 2023-06-30 | 2023-07-08 | 6 | Complete | 100% | bar: 2023-07-03
20 | Design and Engineering | Eric | 2023-06-28 | 2023-07-05 | 6 | Complete | 100% | bar: 2023-07-03
21 | Safety and Standards | Laura | 2023-06-24 | 2023-06-30 | 5 | Complete | 100% | bar: 2023-06-26
23 | Chapter 3: Methodology | Tom | 2023-06-24 | 2023-07-09 | 10 | Complete | 100% | bar: 2023-07-03
24 | Simulation | Eric | 2023-06-24 | 2023-06-27 | 2 | Complete | 100% | bar: 2023-06-26
25 | Prototype Design | Group Work | 2023-06-24 | 2023-06-28 | 3 | Complete | 100% | bar: 2023-06-26
| August Semester Break |  | 2023-08-06 | 2023-09-04 | 21 | Blocked | 100% | bar: 2023-09-04
27 | Chapter 4: Project Implementation
28 | Interfacing STM32 with L298N and Motor | Group Work | 2023-09-14 | 2023-09-14 | 1 | Complete | 100% | bar: 2023-09-11
29 | Interfacing STM32 with L298N, Motor and Relay | Group Work | 2023-09-14 | 2023-09-14 | 1 | Complete | 100% | bar: 2023-09-11
30 | Interfacing STM32 with GSM SIM7600CE | Group Work | 2023-09-21 | 2023-09-22 | 2 | Complete | 100% | bar: 2023-09-18
31 | STM32 with GSM, L298N, Motor and Relay | Group Work | 2023-09-21 | 2023-09-22 | 2 | Complete | 100% | bar: 2023-09-18
32 | WPT Coils design and and testing | Group Work | 2023-09-21 | 2023-09-22 | 2 | Complete | 100%
33 | Interfacing STM32 with IR Sensor Receivers | Group Work | 2023-09-28 | 2023-09-29 | 2 | Complete | 100% | bar: 2023-09-25
34 | STM32+GSM+L298N+Motor+Relay+IR Receivers | Group Work | 2023-09-28 | 2023-09-29 | 2 | Complete | 100% | bar: 2023-09-25
35 | Complete SevWCS Transmitter (Tx) Setup | Group Work | 2023-09-28 | 2023-09-29 | 2 | Complete | 100% | bar: 2023-09-25
36 | Interfacing UNO with MFRC522 RFID Module | Group Work | 2023-10-05 | 2023-10-05 | 1 | Complete | 100% | bar: 2023-10-02
37 | Interfacing UNO with 1602 LCD Display | Group Work | 2023-10-05 | 2023-10-05 | 1 | Complete | 100% | bar: 2023-10-02
38 | Interfacing UNO with IR Sensor Transmitters | Group Work | 2023-10-05 | 2023-10-05 | 1 | Complete | 100% | bar: 2023-10-02
39 | Complete SevWCS Receiver (Rx) Setup | Group Work | 2023-10-05 | 2023-10-05 | 1 | Complete | 100% | bar: 2023-10-02
40 | Testing the Tx Setup with the Rx Setup | Group Work | 2023-10-05 | 2023-10-05 | 1 | Complete | 100% | bar: 2023-10-02
41 | 3D Design of Assembly Parts | Group Work | 2023-10-06 | 2023-10-07 | 1 | Complete | 100% | bar: 2023-10-02
42 | Electric Bus Model Design and Fabrication | Group Work | 2023-10-08 | 2023-10-09 | 1 | Complete | 100% | bar: 2023-10-09
43 | Deployment Wooden Board Design | Group Work | 2023-10-09 | 2023-10-10 | 2 | Complete | 100% | bar: 2023-10-09
44 | Fabrication of the Wooden Board | Group Work | 2023-10-12 | 2023-10-12 | 1 | Complete | 100% | bar: 2023-10-09
45 | 3D Printing of Assembly Parts | Group Work | 2023-10-12 | 2023-10-12 | 1 | Complete | 100% | bar: 2023-10-09
46 | Controlling the WPT Coils using the Tx Setup | Group Work | 2023-10-26 | 2023-10-26 | 1 | Complete | 100% | bar: 2023-10-23
47 | WPT Coils + Tx Setup + Rx Setup | Group Work | 2023-10-26 | 2023-10-26 | 1 | Complete | 100% | bar: 2023-10-23
48 | Final SevWCS Prototype Assembly & Testing | Group Work | 2023-10-26 | 2023-10-26 | 1 | Complete | 100% | bar: 2023-10-23
49 | Preparing Prototype for Presentation | Group Work | 2023-11-02 | 2023-11-02 | 1 | Complete | 100% | bar: 2023-10-30
50 | Completing Chapter 3 of the Final Report | Group Work | 2023-11-09 | 2023-11-10 | 2 | Complete | 100% | bar: 2023-11-06
51 | Final Consultation with the Supervisor | Group Work | 2023-11-16 | 2023-11-16 | 1 | Complete | 100% | bar: 2023-11-13
52 | Presentation | Group Work | 2023-11-23 | 2023-11-24 | 2 | Complete | 100% | bar: 2023-11-20
# | GROUP MEMBERS |  | KEY
1 | Eric Mulwa E021-01-0694/2019 0796456877 |  |  | Completed
2 | Esther Mukite E021-01-0716/2019 0757737763 |  |  | Not Started
3 | Tom Ndolo E021-01-0693/2019 0707377751 |  |  | In Progress
| Supervisor: Dr. Agnes Wangai 0702021687 |  |  | Blocked
|  |  | u | Completion date
|  |  | Statuses |  | FALSE
|  |  | Not started |  | FALSE | FALSE
|  |  | In progress |  | FALSE | FALSE
Blocked
Complete
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))

## Sheet2 (hidden)
2023-03-06
| Project Start Date | 2023-03-06 | [5 empty] | 2023-03-06 | [25 empty] | 2023-04-01 | [29 empty] | 2023-05-01 | [29 empty] | 2023-05-31 | [29 empty] | 2023-06-30 | [29 empty] | 2023-07-30 | [29 empty] | 2023-08-29 | [29 empty] | 2023-09-28 | [29 empty] | 2023-10-28 | [29 empty] | 2023-11-27 | [29 empty] | 2023-12-27 | [29 empty] | 2024-01-26 | [29 empty] | 2024-02-25 | [29 empty] | 2024-03-26 | [29 empty] | 2024-04-25 | [29 empty] | 2024-05-25 | [29 empty] | 2024-06-24 | [29 empty] | 2024-07-24
| Project Name: | Enter Your Project Name |  |  |  |  | Week starting | time axis 2023-03-06 to 2024-08-22
# | Activity | Assigned To | Start | End | Days | Status | % Done
1 | Project Kick-off | Assignee name | 2023-07-02 | 2023-08-31 | 44 | Not started | 0% | bar: 2023-08-28
2 | Project task | John | 2023-04-20 | 2023-07-10 | 58 | In progress | 60% | bar: 2023-07-10
3 | Task 3 | James | 2023-05-10 | 2023-10-23 | 119 | In progress | 20%
4 | Task 4 | Kate | 2023-05-08 | 2023-07-04 | 42 | Blocked | 60% | bar: 2023-07-03
5 | Task 5 | Michael | 2023-04-22 | 2023-07-14 | 60 | Complete | 100% | bar: 2023-07-10
6 | Task 6 | Anna | 2023-02-01 | 2023-10-06 | 178 | In progress | 50%
7 | Task 7 | Peter | 2023-03-01 | 2023-07-06 | 92 | Complete | 100% | bar: 2023-07-03
8 | Task 8
9 | Task 9
10 | Task 10
| Statuses |  | FALSE
| Not started |  | FALSE | FALSE
| In progress |  | FALSE | FALSE
Blocked
Complete
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))